## Work progress tracker (3)
Category | Project Name | Work item | Assigned to | Facility | Process | Description | Start date | Due date | Progress | Notes | Document Shared Link | Attachments
["Internal Procedure"] | PRE-CONFIRMATION PROCEDURE probation | Ryan's Probation Review | Jimmy Chi |  | Other |  | 05/03/2022 | 05/31/2022 | In progress |  |  | 0
["Industrial Engineering"] | 2022 ~ 2023 Lease Extension | Company Signed Up | Jasmine Lin | ["TNN FSL"] | Other | Internal Process | 04/19/2022 | 06/24/2022 | In progress | 5/20 On hold due to business decision 5/9 Back to NK 4/25 Send contract to NK 4/21 Coupa Upload completed, pending on Lease arrival 4/20 Submit COUPA Access right |  | 0
["Industrial Engineering"] | 2023 ~ 2025 Lease Extension | Submit RFA / Contract Signed Up | Elaine Huang | ["LiouFu Facility"] | Whole Operation | Refer to ACC | 03/07/2022 | 06/27/2022 | In progress | 4/29 ACC Approved, pending on RE negotiation 3/21 ACC Submission | https://acc.inside.ups.com/ACC/Apps/ViewAppropriation/ViewAppropriation?AppropID=245899 | 0
["Industrial Engineering"] | 2F High Shelving Density Solution | Be familiar with order picker and check bins | Jasmine Lin | ["Suku Facility"] | Storage Capacity | 1. Check order picker 2. How many bins are there for now? | 11/22/2021 | 12/13/2021 | Blocked |  | https://www.amazon.com/APOLLOLIFT-Propelled-Electric-Picker-reachable/dp/B086TZCKZN/ref=asc_df_B086TZCKZN?tag=bingshoppinga-20&linkCode=df0&hvadid=80539337326258&hvnetw=o&hvqmt=e&hvbmt=be&hvdev=c&hvlocint=&hvlocphy=&hvtargid=pla-4584138868625141&psc=1 | 0
["Industrial Engineering"] | 2F Pallet => Grounding | Check how many pallet can be stored in Pallet | Elaine Huang | ["LiouFu Facility"] | Storage Capacity |  | 11/15/2021 | 11/16/2021 | Completed | 100 板可以上RCK |  | 0
["Industrial Engineering"] | 4F Clean Area work station design & setup | Confirm equipment list and design work station | Jasmine Lin | ["Suku Facility"] | Whole Operation |  | 11/08/2021 | 11/17/2021 | Completed |  |  | 0
["Industrial Engineering"] | 4F Racking Design | 4F Racking Design for AGS REG & ASM | Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 12/01/2021 | 12/17/2021 | Completed |  |  | 0
["Industrial Engineering"] | 4F Racking Design | Design EPG Storage Area | Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 11/25/2021 | 11/29/2021 | Completed |  |  | 0
["SmartView"] | ACDC Shipment Create Database | Requirement Understanding | Dragon Kao | ["NK Facility"] | Admin / Import & Export | Copy from AMT Shipment Create Database But need to know the rule for HAWB first | 11/08/2021 | 11/22/2021 | Completed |  |  | 0
["SmartView"] | ACDC Shipment Create Database | Database Build Up | Dragon Kao | ["NK Facility"] | Admin / Import & Export | Mapping forwarder and publish via PGI hourly mail | 11/22/2021 | 02/25/2022 | Completed | 1. build up HAWB rule preview version. | /:f:/g/personal/00000013598_ups_com/ElUWzLk1VTpKiCDEWhC0i3ABpgkeT19a1Q8NZGqVH_3OOg?e=fXOiYl | 0
["SmartView"] | ACDC Shipment Create Database | Re-build up ACDC Shipment Create System | Dragon Kao | ["NK Facility"] | Admin / Import & Export |  | 11/01/2021 | 05/27/2022 | In progress | 5/27 Issue report back 5/11 First version release | /:p:/r/personal/00000188640_ups_com/_layouts/15/Doc.aspx?sourcedoc=%7B5D910AF0-45ED-4D4F-ABB9-514EABDD5D3F%7D&file=Internal%20AGS%20Review_2022.pptx&action=edit&mobileredirect=true | 0
["RPA"] | Admin Create Invoice Robot | Build-up RPA Bot for Admin Operation | Ryan Chi | ["NK Facility"] | Admin / Import & Export | Robot to run 3 system: SAP, ILC, Access | 04/18/2022 | 05/29/2022 | Blocked | 4/25 Provide designed process |  | 0
["Industrial Engineering"] | AMAT RFP Presentation | NK3 Slide Revised | Jimmy Chi | ["NK Facility"] | Whole Operation |  | 11/09/2021 | 11/10/2021 | Completed |  |  | 0
["RPA"] | ASM Order Creation Robot | Robot Build Up | Ryan Chi | ["LiouFu Facility"] | Outbound / GI |  | 01/24/2022 | 05/27/2022 | Completed | 5/3 2nd Review with Hank 4/18 Review with Hank already, need to do minor modification |  | 0
["Industrial Engineering"] | Audit Monotoring | Check operation one hour per day | Elaine Huang | ["NK Facility"] | Inbound / GR | Daily review operation process | 11/08/2021 | 12/10/2021 | Completed |  |  | 0
["Industrial Engineering"] | Case to People Pilot Project | Draft RFA | Jimmy Chi | ["NK Facility"] | Whole Operation |  | 11/01/2021 | 11/26/2021 | Completed |  |  | 0
["Internal Procedure"] | CDP/CV Update | Update CDP/CV | Jimmy Chi | ["APAC"] | Other |  | 05/09/2022 | 05/11/2022 | Completed |  |  | 0
["Industrial Engineering"] | Company Signed Up Request | Company Signed Up | Elaine Huang | ["TNN FSL","Suku Facility"] | Other | 1. 個資告知書 2. Suku房東意向書 | 04/08/2022 | 04/26/2022 | Completed | 4/21 收到完成文件, 已寄出 4/18 用印申請書完成, 送去大南路 |  | 0
["Industrial Engineering"] | DRS Rebuild | Need to publish new DRS with additional function | Jasmine Lin | ["Suku Facility"] | Whole Operation | 1. Build up DRS to validate actual space 2. Add Scorecard Function into heatmap 3. Add Billing Function into heatmap 4. Add Forecast transaction into heatmap 5. Add Forecast Occupied Space into heatmap | 12/20/2021 | 06/02/2022 | In progress | (5/26 Forecast Occupied Space Complete) (5/12 Forecast Transaction Complete) 5/9 Original Est. Billing Function Completed 4/14 DRS & Scorecard Function Complete | https://upsinc.sharepoint.com/:x:/s/APACCL_Industrial-Engineering/ETmAn39auohIraOLhdlv2NMBM0Ft-b8ZTkv4G2GzZW-AQg?email=linjasmine%40ups.com&e=XIVy7k | 0
["Industrial Engineering"] | EPG Hall1 expansion | Layout Design | Jasmine Lin | ["KaoHsiung EPG Facility"] | Whole Operation |  | 05/13/2022 | 05/18/2022 | Completed | 5/18 Logic review and Deck delivered | https://upsinc.sharepoint.com/:f:/r/sites/APACCL_Industrial-Engineering/Shared%20Documents/TW%20CL%20Database/New%20Business%20Implementation/2022%20Apr%20EPG%20FTZ%20Expansion?csf=1&web=1&e=CbypPq | 0
["Industrial Engineering"] | EPG&TNN FSL Non-bond Space Requirement | Provide proposal to Solution and Operation | Jasmine Lin | ["KaoHsiung EPG Facility","TNN FSL"] | Storage Capacity | Per call, need Jasmine action : 1) Understand the size of EPG NB parts that currently stored in TMC1 2) Evaluate q’ty of moveable shelving required if we have those parts move pack to P8960 (wooden crates area) 3) Evaluate space size of P8960 wooden crates area (is it able to meet 1800 sq ft?) 4) Site tour to TransPac building G 5) Are we able to store P8960 wooden crates to TransPac facility (1800 sq ft) After all these done, we’ll need : a) Layout plan in P8960 for EPG NB parts b) Layout plan for P8960 in TransPac facility c) Storage equipment required for EPG NB parts in P8960 | 04/18/2022 | 05/16/2022 | Completed | 5/20 Close as no further request (5/12 Publish Estimate Project Timeline) 5/10 Movable cart quotation to Andy 5/3 Proposal Presentation to EPG and NK already 4/30 2nd Proposal Delivered 4/26 1st Proposal Delivered 4/20 TNN FSL Site Survey 4/21 TMC1 Site Survey 4/21 Proposal Structure Discussion 4/22 TransPac Site Survey 4/25 Proposal Sharing in EPG weekly call | https://upsinc.sharepoint.com/:f:/r/sites/APACCL_Industrial-Engineering/Shared%20Documents/TW%20CL%20Database/New%20Business%20Implementation/2022%20Apr%20EPG%20Nonbond%20Space%20Proposal?csf=1&web=1&e=IbpVk8 | 0
["SmartView"] | FSL Receiving Scorecard v2.0 | Revised FSL Receiving Mail Notice | Dragon Kao | ["TXG FSL","TNN FSL"] | Inbound / GR | Add 1 more column for Uncontrollable Package (CN Part) | 11/08/2021 | 11/12/2021 | Completed |  |  | 0
["Industrial Engineering"] | Geek+ Implementation in NK Facility | Pilot Project Implement | Jimmy Chi | ["NK Facility"] | Storage Capacity | 1. Contract send to Legal and BaSE for seeking input 2. Racking n Shelving n Carton Quotation Spec check, collect Carton 3. Confirm Pilot Scope with Geek+ 4. Discuss if no system support, can this system run isolated | 05/08/2022 | 06/03/2022 | In progress | 5/24 Send contract back to Geek+ (5/16 Present Implementation Plan and highlight barrier) 5/13 Meeting with Geek+ to confirm Pilot Project Scope 5/9 Kick-off Meeting with Henry |  | 0
["Industrial Engineering"] | Geek+ Implementation in SPLUS | SPLUS Account run by Geek+ Solution | Jimmy Chi | ["LiouFu Facility"] | Storage Capacity | Geek+ can provide lease solution to UPS, they want to arrange site visit to see if they can have quick implementation in LF warehouse | 04/21/2022 | 06/06/2022 | In progress | 5/25 Have 1st meeting with Geek+ for Solution Discussion, Need to check with ACME for structure issue 4/27 UPS should provide layout and related document to Geek+ 4/22 Site survey arrange on 4/27 |  | 0
["SmartView"] | GI Team Delivery | Requirement Understanding | Elaine Huang | ["Suku Facility"] | Outbound / GI |  | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | GI Team Delivery | Document Preparation | Sam Chang | ["Suku Facility"] | Outbound / GI | Operation Owner: Shawn | 10/22/2021 | 10/29/2021 | Completed |  |  | 0
["SmartView"] | GI Team Delivery | Development | Sam Chang | ["Suku Facility"] | Outbound / GI |  | 11/25/2021 | 12/09/2021 | Completed |  |  | 0
["SmartView"] | GI Team Delivery | Implementation and Monitoring | Sam Chang | ["Suku Facility"] | Outbound / GI |  | 12/10/2021 | 01/28/2022 | Completed |  |  | 0
["SmartView"] | GR Line Notice Fixing | Fixed GR Line Robot | Dragon Kao | ["NK Facility"] | Inbound / GR |  | 11/08/2021 | 11/15/2021 | Completed |  |  | 0
["Industrial Engineering"] | GR Reengineering | Prepare weekly call slide | Jasmine Lin | ["Suku Facility"] | Inbound / GR |  | 11/29/2021 | 11/30/2021 | Completed | Weekly Call Follow Up |  | 0
["SmartView"] | GR Tool v2.0 | Process Understanding | Sam Chang | ["NK Facility"] | Inbound / GR |  | 10/25/2021 | 11/05/2021 | Completed |  |  | 0
["SmartView"] | GR Tool v2.0 | Tool Development | Sam Chang | ["NK Facility"] | Inbound / GR |  | 11/15/2021 | 04/01/2022 | Completed | the GR Tool only in IE work, when Chrome, Edge will not work, is Active-X object issue, the Chrome browser default disable the object, and can not enable. |  | 0
["SmartView"] | GR Tool v2.0 | Implementation and Monitoring | Sam Chang | ["NK Facility"] | Inbound / GR |  | 03/03/2022 | 05/31/2022 | In progress | (Plan to close on 5/16 originally) Refer to weekly update | /personal/00000188640_ups_com/Documents/Internal%20AGS%20Review_2022.pptx?web=1 | 0
["SmartView"] | GR Tool v2.0 | T1 T2 Database Build Up | Dragon Kao | ["NK Facility"] | Inbound / GR | from mail to SmartView Database | 11/30/2021 | 12/10/2021 | Completed |  |  | 0
["SmartView"] | GR Tool v2.0 | Function 1. TR Auto Print TO | Sam Chang | ["NK Facility"] | Inbound / GR |  | 12/20/2021 | 12/31/2021 | Completed |  |  | 0
["SmartView"] | GR Tool v2.0 | Function 2. Cancel TO + Create TO | Sam Chang | ["NK Facility"] | Inbound / GR |  | 01/03/2022 | 01/28/2022 | Completed |  |  | 0
["SmartView"] | GR Tool v2.0 | Function 3. +Q | Sam Chang | ["NK Facility"] | Inbound / GR |  | 01/17/2022 | 01/28/2022 | Completed |  |  | 0
["SmartView"] | GR Tool v2.0 | Function 4. Print Unit Label | Sam Chang | ["NK Facility"] | Inbound / GR |  | 01/24/2022 | 01/28/2022 | Completed |  |  | 0
["Industrial Engineering"] | GR Tool v2.0 | Movable Workstation Desgin | Elaine Huang | ["NK Facility"] | Inbound / GR | Co-work with Sam and James to design movable workstation | 12/20/2021 | 01/07/2022 | Blocked |  |  | 0
["SmartView"] | GR Tool v2.0 | Function 5. Audit Mapping with T1 T2 file | Sam Chang | ["NK Facility"] | Inbound / GR |  | 01/31/2022 | 02/18/2022 | Blocked |  |  | 0
["Internal Procedure"] | HK TW Facilities LED | Support BaSE complete research | Jimmy Chi | ["NeiHu FSL","LiouFu Facility","NK Facility","TXG FSL","TNN FSL","Suku Facility","KaoHsiung EPG Facility"] | Other |  | 05/06/2022 | 05/09/2022 | Completed |  |  | 1
["SmartView"] | HR 的出缺勤報表整理 | Requirement Understanding | Sam Chang | ["Suku Facility"] | Admin / Import & Export |  | 12/02/2021 | 12/09/2021 | Blocked |  |  | 0
["SmartView"] | ILC & SAP 庫存比對 | Requirement Understanding | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | ILC & SAP 庫存比對 | Document Preparation | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | ILC & SAP 庫存比對 | Development | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | ILC & SAP 庫存比對 | Implementation and Monitoring | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | IS Dashboard - Issue Status View | Wrong QA List | Dragon Kao | ["NK Facility"] | Inventory Specialist |  | 11/04/2021 | 11/11/2021 | Completed | Finish Create View, hold meeting with Wade, Wade request add description on the view, | http://uwkp000c5727:8080/IS/IssueStatus | 0
["SmartView"] | IS Dashboard - Issue Status View | Add Criteria statement in the view | Sam Chang | ["NK Facility"] | Inventory Specialist |  | 11/04/2021 | 11/11/2021 | Completed |  |  | 0
["SmartView"] | IS Dashboard - Issue Status View | Fixed Image issue | Sam Chang | ["NK Facility"] | Inventory Specialist |  | 11/04/2021 | 11/09/2021 | Completed |  |  | 0
["SmartView","Industrial Engineering"] | IS Dashboard - PPH View | Achieve Rate modification | Sam Chang | ["NK Facility"] | Inventory Specialist | 1. Change format to percentage 2. Set color according to achieve rate 3. IS , Shipping, Receiving done | 11/08/2021 | 11/30/2021 | Completed |  |  | 0
["SmartView"] | IS Reporting Automation | List done what report will be under SmartView | Sam Chang | ["NK Facility"] | Inventory Specialist | 因應Critix 項目的執行,如果AMAT將UPS登入SAP的權限收回 將會影響到IS目前的9隻Daily Report 以及3隻Weekly Report 如果確定收回後,IS約需要增加每天1~1.5個人力在這些Report事項上 | 06/08/2022 | 06/24/2022 | In progress |  |  | 1
["RPA"] | JAS Robot | Build up RPA Bot to support UPS Clark Billing and Transport Team | Ryan Chi | ["APAC"] | Admin / Import & Export | PPT was presented to Ryan for the step by step process of JAS – CL, SP and FF | 03/09/2022 | 06/15/2022 | In progress | 4/29 CL Review Meeting, Working on: SP 4/14 CL Complete, Remaining Part: SP & FF |  | 0
["RPA"] | Kitting Checking Tool | Tool Modify | Ryan Chi | ["NK Facility"] | Other |  | 03/10/2022 | 03/10/2022 | Completed |  |  | 0
["SmartView"] | Kitting Dashboard | Shipping View Build Up | Dragon Kao;Sam Chang | ["NK Facility"] | Whole Operation |  | 11/05/2021 | 11/12/2021 | Completed |  |  | 0
["SmartView"] | Kitting Dashboard | Receiving Dock-in Notice | Dragon Kao | ["NK Facility"] | Whole Operation |  | 11/05/2021 | 12/17/2021 | Completed |  |  | 0
["SmartView"] | Kitting Dashboard | Kitting CQP list Mapping with Serial number input | Dragon Kao;Ryan Chi | ["NK Facility"] | Other | Anna request need solution to speed up the operation mapping data from SAP and Access , and add new function for check input serial number. | 12/22/2021 | 03/31/2022 | Completed | 1. build up VBA finish , waiting operation test |  | 1
["SmartView"] | Kitting Dashboard | CQP List file 2nd Modify | Ryan Chi | ["NK Facility"] | Other | Revised bug in existing file | 01/21/2022 | 01/26/2022 | Completed |  |  | 0
["RPA"] | Kitting Dashboard | Picking and CQP Process Redesign - Process Understanding | Ryan Chi | ["NK Facility"] | Other | Operation to provide MiniJBA or SOP first | 04/04/2022 | 04/29/2022 | Blocked |  |  | 0
["Industrial Engineering"] | Lease Renew | Taichung 2022~2027 5 Years Renew | Elaine Huang | ["TXG FSL"] | Other | 1. Submit RFA for budget approval 2. Signed Company chop | 03/21/2022 | 05/27/2022 | In progress | 4/25 Country REFCO 4/20 Draft RFA 4/15 Andy collect all required quotation 4/6 Pending to May REFCO |  | 0
["Industrial Engineering"] | LiuoFu REG add RCK Layout Design | Layout Design by Spare Material | Elaine Huang | ["LiouFu Facility"] | Other |  | 11/29/2021 | 01/07/2022 | Blocked |  |  | 0
["Industrial Engineering"] | LiuoFu REG add RCK Layout Design | Revised saving Space | Elaine Huang | ["LiouFu Facility"] | Storage Capacity |  | 12/13/2021 | 12/14/2021 | Completed |  |  | 0
["Industrial Engineering"] | LiuoFu REG add RCK Layout Design | Work with vendor to check if spare material can be used | Elaine Huang | ["LiouFu Facility"] | Storage Capacity |  | 12/13/2021 | 12/17/2021 | Completed |  |  | 0
["Industrial Engineering"] | Long Rack Usage Enhancement | Customer raise challenge of low usage racking | Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 04/08/2022 | 05/27/2022 | Completed | Handover to OP and monitor in Scorecard |  | 0
["Industrial Engineering"] | LSS Presentation | Presentation Preparation | Jimmy Chi | ["NK Facility"] | Other |  | 11/05/2021 | 11/09/2021 | Completed |  | https://wss.inside.ups.com/sites/APIE/Logistics/TWCL/Shared%20Documents/LSST%20Training%20Green%20Belt%20Project%20Slide%20-%20Team%20AGS_0.pptx?web=1 | 0
["Industrial Engineering"] | LSS Presentation | 2nd Round Modification | Jimmy Chi | ["NK Facility"] | Other |  | 11/11/2021 | 11/12/2021 | Completed |  |  | 0
["Industrial Engineering"] | LSS Presentation | Modified and Draft script | Jimmy Chi | ["NK Facility"] | Other |  | 11/12/2021 | 11/16/2021 | Completed | https://wss.inside.ups.com/sites/APIE/Logistics/TWCL/Shared%20Documents/LSST%20Training%20Green%20Belt%20Project%20Slide%20-%20Team%20AGS_1.pptx?web=1 |  | 0
["Industrial Engineering; SmartView"] | Merge Productivity Enhancement - Merge Tool | Requirement Understanding | Elaine Huang | ["NK Facility"] | Outbound / GI |  | 10/25/2021 | 10/29/2021 | Completed |  |  | 0
["Industrial Engineering; SmartView"] | Merge Productivity Enhancement - Merge Tool | Concept Discussion and Design | Elaine Huang | ["NK Facility"] | Outbound / GI |  | 10/25/2021 | 10/29/2021 | Completed |  |  | 0
["SmartView","Industrial Engineering"] | Merge Productivity Enhancement - Merge Tool | Benefit Evaluation | Elaine Huang | ["NK Facility"] | Outbound / GI | This week Dragon finish color bar(11/19) Send File to Jimmy 11/22 | 11/01/2021 | 11/22/2021 | Completed |  |  | 1
["Industrial Engineering","SmartView"] | Merge Productivity Enhancement - Merge Tool | Tool Database Development | Dragon Kao | ["NK Facility"] | Outbound / GI |  | 10/25/2021 | 11/05/2021 | Completed | Build up database, setup step 1. http://uwkp000c5727:5050/GET/Shipping/getPickupMasterStatus/234390F1-9D80-4E51-B5A3-65A10C72FF35 to get information and status set Step2. http://uwkp000c5727:5050/POST/Shipping/setPickupSubItemInformation/234390F1-9D80-4E51-B5A3-65A10C72FF35/pallet1 assign pallet |  | 0
["Industrial Engineering","SmartView"] | Merge Productivity Enhancement - Merge Tool | GUI Development | Dragon Kao | ["NK Facility"] | Outbound / GI |  | 11/08/2021 | 11/23/2021 | Completed |  |  | 0
["Industrial Engineering","SmartView"] | Merge Productivity Enhancement - Merge Tool | Implementation and Monitoring | Elaine Huang;Dragon Kao | ["NK Facility"] | Outbound / GI | 1. Database build up - done 2. build up test version 2-1. create simple view - done 2-2. add script to check user scan id/ pallet process 2-3. create HTML Grid control action from script | 11/22/2021 | 06/01/2022 | In progress | (5/13 Desktop completed, handover to Dragon) 5/3 Publish loot cause to OP and pending on H/W setup 4/25 Publish a mail to Dennis and Kathia, aim to close project on 5/17 4/20 Need to confirm handover time |  | 0
["SmartView","Industrial Engineering"] | Merge Productivity Enhancement - Merge Tool | Modify Admin Access to create QR code | Dragon Kao | ["NK Facility"] | Outbound / GI |  | 11/30/2021 | 11/30/2021 | Completed |  |  | 0
["SmartView"] | Micron Material Number Mapping Tool | Data Matrix | Jimmy Chi | ["NK Facility"] | Outbound / GI |  | 11/29/2021 | 12/03/2021 | Completed |  |  | 0
["RPA","Industrial Engineering"] | NeiHu Facility Heat Map | Report Build up | Elaine Huang;Ryan Chi | ["NeiHu FSL"] | Inventory Specialist |  | 07/01/2022 | 07/15/2022 | Not started | Start After NeiHu FSL Relocation Completed |  | 0
["Industrial Engineering"] | NeiHu FSL RFA | Prepare New RFA for Rental New Facility | Elaine Huang | ["NeiHu FSL"] | Other |  | 11/29/2021 | 01/28/2022 | Completed |  |  | 0
["Internal Procedure"] | NewsLetter Preparation | Survey if we can use Page Tiger to deliver NewsLetter | Elaine Huang;Jasmine Lin |  | Other | Henry want to use Page Tiger to deliver NewsLetter | 05/04/2022 | 05/16/2022 | Completed | 5/16 Let Henry know the price already: annual 600 USD, waiting for his advise 5/5 Sent the message to IE Training Help team and see if they can share us some information how to start | https://ups.pagetiger.com/view-newsletter/april-2022 | 0
["Industrial Engineering"] | NK3 Facility Preparation | Design and Completer RFA Process | Jimmy Chi | ["New Facility","NK Facility","LiouFu Facility"] | Whole Operation |  | 03/14/2022 | 06/17/2022 | In progress | 4/21 Submit RFA in ACC 4/14 AP REFCO Review | https://acc.inside.ups.com/ACC/Apps/ViewAppropriation/ViewAppropriation?AppropID=248139 | 0
["Industrial Engineering"] | NK3 Facility Preparation | ShanLin ver 2 Layout Design | Jimmy Chi;Elaine Huang | ["New Facility"] | Whole Operation | Due to 地目 and regularity, facility will shrink and need to re-do layout for customer proposal | 04/14/2022 | 05/23/2022 | Completed | 5/30 Complete Kitting Forecast - No Impact 5/19 Present to Rick 5/17 Present to Mark 5/13 Final Deck Delivered 5/5 Present to Applied Material Already 4/25 Receive New CAD and need to redo layout 4/22 Discuss feasibility with Geek+ 4/21 first draft provided |  | 0
["Industrial Engineering"] | Nokia Process Review | Current PPH Collect | Elaine Huang | ["LiouFu Facility"] | Whole Operation | Ally provide working hour--11/9 Ian provide daily transaction--11/12 Actual PPH Cal.---11/12 Time Study and Finding --11/15 Setup Plan PPH--- 11/17 | 11/08/2021 | 12/06/2021 | Completed | • Storage Issue- estimate complete date: 11/29. • Receiving Checking List- estimate complete date: 11/26. • Layout and traffic flow issue- estimate complete date: 11/30. |  | 1
["SmartView"] | OC On Duty Dashboard | Request Understanding | Jimmy Chi | ["NK Facility"] | Other |  | 03/09/2022 | 03/21/2022 | Completed |  |  | 0
["SmartView"] | Outbound Delivery Report | Requirement Understanding | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | Outbound Delivery Report | Document Preparation | Sam Chang | ["Suku Facility"] | Admin / Import & Export | Operation Owner - Jessie Lin | 10/21/2021 | 10/22/2021 | Completed |  |  | 0
["SmartView"] | Outbound Delivery Report | Development | Sam Chang | ["Suku Facility"] | Admin / Import & Export |  | 11/08/2021 | 11/11/2021 | Completed |  |  | 1
["SmartView"] | Outbound Delivery Report | Implementation and Monitoring | Sam Chang | ["Suku Facility"] | Admin / Import & Export |  | 11/10/2021 | 11/24/2021 | Completed |  |  | 0
["Industrial Engineering"] | Outbound Delivery Report | Check purpose of this activity and if AGS has such operation | Jimmy Chi;Jasmine Lin | ["Suku Facility"] | Admin / Import & Export |  | 11/05/2021 | 11/11/2021 | Completed |  |  | 0
["Industrial Engineering"] | PPH Implementation | Receiving/GR Plan PPH Define | Jasmine Lin | ["Suku Facility"] | Inbound / GR | Time Study | 11/01/2021 | 12/01/2021 | Completed |  |  | 0
["Industrial Engineering"] | PPH Implementation | PPH Implementation | Jasmine Lin | ["Suku Facility"] | Whole Operation |  | 11/08/2021 | 01/31/2022 | Blocked | 誰一天做多少,結合SAP表單,花多少時間做 |  | 0
["Industrial Engineering"] | PPH Implementation | Check where to get daily completed volume | Jasmine Lin | ["Suku Facility"] | Inbound / GR | 有User ID尤佳 | 12/01/2021 | 12/10/2021 | Blocked |  |  | 0
["Industrial Engineering"] | PPH Implementation | Shipping/GI Plan PPH Define | Jasmine Lin | ["Suku Facility"] | Outbound / GI |  | 11/30/2021 | 01/21/2022 | Completed |  |  | 0
["Industrial Engineering"] | PPH Tracker - New Function | Add weekly PPH record as summary | Jimmy Chi | ["NK Facility"] | Inbound / GR |  | 11/03/2021 | 11/10/2021 | Completed |  |  | 0
["Industrial Engineering"] | PPH Tracker - New Function | Add weekly PPH as summary in shipping | Jimmy Chi | ["NK Facility"] | Outbound / GI |  | 11/03/2021 | 11/11/2021 | Completed |  |  | 0
["Industrial Engineering"] | PR Review | G8 PR Review | Jimmy Chi | ["Suku Facility"] | Whole Operation |  | 03/21/2022 | 05/17/2022 | Completed | 5/16 Review Done Pending since 4/12 |  | 0
["SmartView","Industrial Engineering"] | Processing Time Complete Distribution | Free Survey | Elaine Huang;Jasmine Lin;Dragon Kao;Sam Chang | ["Suku Facility","NK Facility"] | Whole Operation |  | 11/01/2021 | 11/30/2021 | Blocked |  |  | 0
["Internal Procedure"] | Progress Tracking Update | Migrate each ppt to here | Jimmy Chi | ["NK Facility"] | Other |  | 11/04/2021 | 11/08/2021 | Completed |  |  | 1
["RPA"] | QR Code Auto Create | Transfer Name to QR Code to reduce IE effort | Ryan Chi | ["NK Facility"] | Other |  | 03/10/2022 | 03/25/2022 | Completed |  |  | 0
["Industrial Engineering"] | R&R Review | Check if front-line UPSer is too much | Jasmine Lin | ["Suku Facility"] | Whole Operation |  | 11/08/2021 | 12/31/2021 | Completed |  |  | 0
["SmartView"] | Receiving Dashboard - Hourly Backlog | Add one graph to Top Page | Sam Chang | ["NK Facility"] | Inbound / GR |  | 05/09/2022 | 05/31/2022 | In progress |  |  | 0
["SmartView"] | Receiving Dashboard - PPH View | Complete Volume Database Build Up | Dragon Kao | ["NK Facility"] | Inbound / GR |  | 11/08/2021 | 12/14/2021 | Completed |  |  | 0
["SmartView"] | Receiving Dashboard - PPH View | View Build Up | Sam Chang | ["NK Facility"] | Inbound / GR | Need color on plan PPH | 11/22/2021 | 12/17/2021 | Completed |  |  | 0
["SmartView"] | Receiving Dashboard - PPH View | Implement and Monitoring | Jimmy Chi | ["NK Facility"] | Inbound / GR |  | 11/22/2021 | 12/21/2021 | Completed |  |  | 0
["SmartView"] | Receiving Dashboard - Putaway Tracker | Database Build Up | Sam Chang | ["NK Facility"] | Inbound / GR |  | 05/24/2022 | 06/07/2022 | In progress | 5/30 2nd Review 5/25 1st Review |  | 0
["Industrial Engineering"] | Receiving Plan PPH Annual Refresh | 2 Weeks Time Study | Elaine Huang | ["NK Facility"] | Inbound / GR |  | 12/01/2021 | 02/28/2022 | Blocked |  |  | 0
["Industrial Engineering"] | Receiving Processing Area Relayout | Requirement Understanding | Elaine Huang | ["NK Facility"] | Inbound / GR | Number of Workstation Demand of Staging Area PPH | 12/01/2021 | 02/28/2022 | Blocked |  |  | 0
["Industrial Engineering"] | Receiving Processing Area Switch to 1F Survey | Layout Design | Jasmine Lin | ["Suku Facility"] | Inbound / GR |  | 11/25/2021 | 12/08/2021 | Blocked |  |  | 0
["Industrial Engineering"] | Receiving Processing Area Switch to 1F Survey | Processing Time Saving Evaluation and Financial Evaluation | Jasmine Lin | ["Suku Facility"] | Inbound / GR |  | 11/29/2021 | 12/08/2021 | Blocked |  |  | 0
["Industrial Engineering"] | REG Storage Enhancement in LiouFu | Check remaining material in LiouFu | Elaine Huang | ["LiouFu Facility"] | Storage Capacity |  | 11/08/2021 | 11/09/2021 | Completed |  |  | 1
["Industrial Engineering"] | Relocation Project | Support Operation relocation project move on and complete | Elaine Huang | ["NeiHu FSL"] | Whole Operation |  | 02/06/2022 | 06/30/2022 | In progress | 5/6 New Site Survey 3/24 Kick-off Meeting 3/18 Fully Approved 2/6 RFA Submit | https://acc.inside.ups.com/ACC/Apps/ViewAppropriation/ViewAppropriation?AppropID=243575 | 0
["SmartView","Industrial Engineering"] | Reverse Dashboard - PPH View | Check cyclecount data source and if it can be collected from SAP directly | Sam Chang;Dragon Kao | ["NK Facility"] | Other |  | 11/08/2021 | 12/03/2021 | Completed |  |  | 0
["SmartView"] | Reverse Dashboard - PPH View | 2nd Development | Sam Chang;Dragon Kao | ["NK Facility"] | Other | Add cyclecount inside Find 543 data in SE17, can try 317 data in SE17 | 11/19/2021 | 12/03/2021 | Completed |  |  | 0
["SmartView","Industrial Engineering"] | Reverse Dashboard - PPH View | Implementation and Monitoring | Sam Chang;Elaine Huang | ["NK Facility"] | Other | Sam, please ensure dashboard result is same as expectation Elaine, please ensure OP is fine with this result and you are good to use | 11/15/2021 | 02/11/2022 | Completed | check data with Vicky the ZAMGR012 data timezone need -16 will maych Vicky data, Cyclecount data waiting Vicky provide 316 cycle count date. |  | 0
["SmartView","Industrial Engineering"] | Reverse Dashboard - PPH View | Create a area for OP to input cyclecount completed volume | Dragon Kao | ["NK Facility"] | Other | translate mail to operation | 01/19/2022 | 01/28/2022 | Blocked |  |  | 0
["RPA"] | Reverse QN Photo Consolidation Robot | Robot Build Up | Ryan Chi | ["NK Facility"] | Other |  | 01/23/2022 | 03/25/2022 | Completed |  | /personal/00000188640_ups_com/Documents/Internal%20AGS%20Review_2022.pptx?web=1 | 0
["Industrial Engineering"] | RFID Implementation | ROI Analysis | Elaine Huang | ["NK Facility"] | Other | Consolidate all solution ROI Analysis---Pending on OP provide required number of tag Wayne will provide information for Tag before Monday(11/22) | 11/08/2021 | 02/28/2022 | Completed | 4/20 On hold due to long paidback time. can re-survey once Applied signed 10 year contract |  | 1
["Industrial Engineering"] | Shelving Hang Part Storage Solution | Check detail with Shaya | Elaine Huang | ["NK Facility"] | Storage Capacity | Shaya詢問木工後,木工不做 轉往詢問鐵工 鐵工Come to survey in 11/19 Jay feed back is need to discuss more with Wade and Dennis | 11/05/2021 | 04/26/2022 | Blocked | 4/26 Close first due to labor resource limitation 4/20 No Progress from OPs |  | 0
["SmartView"] | Shipping Dashboard | 2 day data -> 1 week data | Dragon Kao | ["LiouFu Facility"] | Outbound / GI |  | 11/08/2021 | 11/12/2021 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard | Check when account will be back | Dragon Kao | ["LiouFu Facility"] | Outbound / GI | Hank's account has been suspended, that's why no data refreshed | 11/08/2021 | 11/11/2021 | Completed | check BOBJ the schedule has been delete , re-setup schedule |  | 0
["SmartView"] | Shipping Dashboard | Submit Request For Connect Oracle DB r569 waiting Approved | Dragon Kao | ["LiouFu Facility"] | Outbound / GI |  | 11/12/2021 | 12/06/2021 | Completed | Wait APRS approved |  | 0
["SmartView"] | Shipping Dashboard - Failed Reason Checking Migrate to SmartView Page | Build Up Failed Reason Collect Database | Dragon Kao | ["NK Facility"] | Outbound / GI |  | 01/03/2022 | 01/14/2022 | Blocked |  |  | 0
["SmartView"] | Shipping Dashboard - Failed Reason Checking Migrate to SmartView Page | Add filled in page into SmartView and show in Downs | Dragon Kao | ["NK Facility"] | Outbound / GI |  | 04/25/2022 | 05/10/2022 | Completed | 5/3 Add Remark into Dashboard 4/25 Review Siman's version and see if can use |  | 0
["SmartView"] | Shipping Dashboard - Pick-up View | New Status / New Query Update | Dragon Kao | ["NK Facility"] | Outbound / GI |  | 11/08/2021 | 11/08/2021 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - Pick-up View | Review Meeting | Sam Chang | ["NK Facility"] | Outbound / GI | meeting change to 11/23 | 11/08/2021 | 11/22/2021 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - Pick-up View | Meeting | Sam Chang | ["NK Facility"] | Outbound / GI | 1. 89都該要已放行, 因為不用放行 2. 改format的icon 3. bond & non-bond - 用TO來看 | 01/11/2022 | 01/18/2022 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - Pick-up View | 放行狀態的更新 | Sam Chang | ["NK Facility"] | Outbound / GI | 放行狀態是抓C1 C2 / C3要抓出倉資料才能代表是不是有放行 Picked-up View有沒有更改到C2/C3放行後也有更新 | 01/19/2022 | 01/25/2022 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - Pick-up View | 保 / 非保 | Sam Chang | ["NK Facility"] | Outbound / GI | 保稅貨會有因為保稅帳不夠扣而有部分料變成非保 | 01/20/2022 | 01/25/2022 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - Pick-up View | Validate top 5 item | Sam Chang | ["NK Facility"] | Outbound / GI | 11347383, 11373346, 11373353, 11374261, 11375029 | 01/19/2022 | 01/26/2022 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - Pick-up View | 保稅/非保稅 欄位位子 | Sam Chang | ["NK Facility"] | Other | 移到Shipment後面 | 01/19/2022 | 01/26/2022 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - PPH View | Complete Volume Database Build Up | Dragon Kao | ["NK Facility"] | Outbound / GI | Nov.18 Finish Shipping Picking actual item Nov.18 Finish Shipping Packing actual item Nov.18 Finish Shipping System actual item Nov.18 add Target Volumn, Actual Item, and Actual PPH to View Nov.22 add Achive Rate to View | 11/08/2021 | 11/26/2021 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - PPH View | View Development | Sam Chang | ["NK Facility"] | Outbound / GI |  | 11/15/2021 | 11/26/2021 | Completed |  |  | 0
["SmartView"] | Shipping Dashboard - PPH View | Implementation and Monitoring | Jimmy Chi | ["NK Facility"] | Outbound / GI | add type check in the table | 11/22/2021 | 02/25/2022 | Completed |  |  | 0
["SmartView"] | Shipping Line GUI to entry Working Time | Build Up Line Robot for Time Card Entry | Dragon Kao | ["NK Facility"] | Outbound / GI |  | 11/08/2021 | 11/29/2021 | Blocked |  |  | 0
["SmartView"] | SmartView RIT Support | Fill in RIT Required Information | Dragon Kao;Sam Chang | ["NK Facility"] | Whole Operation |  | 11/01/2021 | 11/05/2021 | Completed |  | /:x:/g/personal/00000013598_ups_com/EWVavXoc7hlMvv2S_nWW678B6wk68Dt56pDfa89S251V3g?e=4FPiDz | 0
["SmartView"] | SmartView RIT Support | Check Output Requirement | Dragon Kao | ["NK Facility"] | Whole Operation | 1. MB51 2. VL06O | 11/08/2021 | 11/09/2021 | Completed |  |  | 0
["SmartView"] | SmartView RIT Support | Need to talk to IT for firewall issue | Jimmy Chi | ["NK Facility"] | Whole Operation | After received Flora's mail information *JDBC | 11/08/2021 | 12/07/2021 | Completed |  |  | 0
["SmartView"] | SmartView RIT Support | Let Output box has "V" if needed | Dragon Kao | ["NK Facility"] | Whole Operation |  | 11/08/2021 | 11/09/2021 | Completed |  |  | 0
["SmartView"] | SmartView UPS and Applied Material Intergration | Provide Proposal and Data to Applied GIS | Dragon Kao | ["NK Facility"] | Whole Operation |  | 12/21/2021 | 05/27/2022 | In progress | (5/31 Reply Flora) 5/24 Data Element 5th Review 5/18 Data Element 4th Review 5/4 Data element 3rd Review 4/22 Data element 2nd Review 4/21 Data element 1st Review 4/20 Before - Refer to weekly update | https://wss.inside.ups.com/sites/APIE/Logistics/TWCL/claire/_layouts/15/WopiFrame2.aspx?sourcedoc=/sites/APIE/Logistics/TWCL/claire/Shared%20Documents/Applied%20AGS/Applied%20Ops%20(AGS)%2020220419.xlsx&action=default | 0
["Industrial Engineering"] | Spare Material Counting | Counting All Asset | Elaine Huang | ["NK Facility"] | Storage Capacity |  | 11/19/2021 | 02/28/2022 | Completed | 11/19 5 Pallet |  | 0
["SmartView"] | SPLUS Shipping Dashboard | Build up visibility to support operation KPI control | Dragon Kao | ["LiouFu Facility"] | Outbound / GI |  | 03/01/2022 | 06/06/2022 | In progress | 5/30 Check with Hank if he wants to change owner from OPs 5/26 Per Kang, there's no SPLUS Dashboard, SmartView SPLUS is still effect 5/5 2nd Notice 4/26 Kang feedback there's another dashboard for SPLUS, pending on they provide link |  | 0
["Industrial Engineering"] | SPLUS SHTC Request | Co-work with PM team to find out how to request SHTC | Elaine Huang | ["NeiHu FSL"] | Other | Hold meeting with Hank and Jimmy-Review proposal first Hold meeting with Henry, Kenneth- Discuss how to follow | 11/08/2021 | 11/26/2021 | Completed |  |  | 1
["Industrial Engineering"] | Storage Material Cyclecount | Build up Storage Equipment Asset Management | Elaine Huang | ["NK Facility","LiouFu Facility","Suku Facility"] | Storage Capacity |  | 11/08/2021 | 11/19/2021 | Completed |  |  | 0
["Industrial Engineering"] | Suku DRS Report Build Up | Check Data Source | Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 11/08/2021 | 12/02/2021 | Completed |  |  | 0
["Industrial Engineering"] | Suku DRS Report Build Up | AutoCAD installation | Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 11/11/2021 | 11/15/2021 | Completed |  |  | 0
["Industrial Engineering"] | Suku DRS Report Build Up | Measure area and update TW Facility Design information | Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 11/15/2021 | 11/22/2021 | Completed |  |  | 0
["Industrial Engineering"] | Suku DRS Report Build Up | Understand current calculation logic | Jimmy Chi | ["Suku Facility"] | Storage Capacity |  | 11/15/2021 | 11/18/2021 | Completed |  |  | 0
["Industrial Engineering"] | Suku DRS Report Build Up | DRS Build Up | Jimmy Chi;Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 11/18/2021 | 03/22/2022 | Completed |  |  | 0
["Industrial Engineering"] | Suku Facility plan of bins | Check the facility plan of bins by Applied machine’s BOM | Jasmine Lin | ["Suku Facility"] | Storage Capacity |  | 12/01/2021 | 06/03/2022 | In progress | 6/3 Last review 5/16 Review result by heatmap 5/9~13 P2 Bin Movement 4/26 Bin Movement Complete 4/25 Bin Movement Action 4/22 Transfer saving to transaction rate reduction amount 4/22 Vicky agree with Phase 2, need to confirm timeline with OP 4/15 Add more module into Analysis 4/8 Add Production Plan in 4/1 Proposal Completed |  | 0
["Industrial Engineering"] | Suku Facility Relocation | Relocation Reason | Jasmine Lin;Jimmy Chi | ["Suku Facility"] | Other | 1. 地板崩裂, 即使找廠商(展熠)評估, 完成工程後也只能撐一到兩年, 未來每一年都需要額外的維修費用且會越來越多 維修期間也會要兩個月, 影響Operation在做額外的Bin to bin | 01/11/2022 | 07/15/2022 | Blocked |  |  | 0
["Industrial Engineering"] | Suku Weekly Call Minor Item Follow up | 確認第二個人盤點的機率、頻率有多高 | Jasmine Lin | ["Suku Facility"] | Inventory Specialist |  | 11/05/2021 | 11/19/2021 | Completed |  |  | 0
["Industrial Engineering"] | Taiwan Team Space Revenue / Cost Allocation Problem | Align with facility owner and FA to make financial result correct | Jimmy Chi | ["NK Facility","Suku Facility","TNN FSL","LiouFu Facility"] | Storage Capacity | Hold a meeting to discuss with FA, to make sure they can allocate correct | 04/14/2022 | 05/03/2022 | Completed | 5/3 Announcement and handover to OP 4/27 Hold meeting with IT consultant team to align cost allocation, will effect on Apr 4/21 Align with billing team already, publish required action to the team 4/18 Align with Taiwan facility owner already |  | 0
["RPA"] | Thematic Jumpstart Bootcamp | TW CL IE Team Survey and Deliver | Jimmy Chi;Ryan Chi;Elaine Huang | ["NK Facility"] | Whole Operation |  | 05/04/2022 | 07/29/2022 | In progress |  |  | 0
["Internal Procedure"] | Thematic Jumpstart Bootcamp | Power Automate Workshop | Dragon Kao;Jasmine Lin;Sam Chang | ["Suku Facility"] | Whole Operation |  | 05/02/2022 | 07/29/2022 | In progress |  |  | 0
["Industrial Engineering"] | TNN FSL Relocation | Survey if new location can move 8960 + EPG to proposed building | Jasmine Lin | ["TNN FSL"] | Whole Operation |  | 05/10/2022 | 06/17/2022 | In progress | (6/2 RFA Complete) 5/31 Quotation Collect |  | 0
["SmartView"] | Update Facility HeatMap | Check Facility Heat Map as Mapping Rate reduce | Jimmy Chi | ["TXG FSL","NK Facility","LiouFu Facility"] | Storage Capacity | TXG add additional bay NK add Y25 & Y26 | 11/11/2021 | 11/12/2021 | Completed |  |  | 0
["Industrial Engineering"] | UPS Brown Mode and Agent Mode Cost Evaluation | Propose cost comparison to justify which is better | Jasmine Lin | ["Suku Facility"] | Whole Operation |  | 05/09/2022 | 05/23/2022 | Blocked |  |  | 0
["RPA"] | UPS Clark Billing and Transport Team Plan for Automation | Robot Build Up | Ryan Chi |  | Other |  | 03/04/2022 | 04/29/2022 | Blocked |  |  | 0
["Industrial Engineering"] | UPS Facility Design | Measure layout | Elaine Huang | ["NeiHu FSL","KaoHsiung EPG Facility"] | Whole Operation | NeiHu Layout EPG Layout | 11/22/2021 | 11/22/2021 | Completed |  |  | 0
["Industrial Engineering"] | Weekly Summary Document Preparaion | Build up PPH View | Elaine Huang;Sam Chang | ["NK Facility"] | Other | RCV SHP IS RVC Productivity View | 11/25/2021 | 05/27/2022 | In progress | 5/27 Shipping View Delivered 4/20 Review 1. Putaway Type Wrong, need to check 2. GR = GR + Audit + Paste TO 4/20 Shipping PPH View Sharing 4/19 Upload Receiving PPH View to SmartView Website 4/12 Complete Structure |  | 1
["Industrial Engineering"] | XDK Storage Bin | IS team will go for C7 shelving | Elaine Huang | ["NK Facility"] | Inventory Specialist |  | 11/08/2021 | 11/09/2021 | Completed |  |  | 0
["Industrial Engineering"] | Z Area Layer Added | Check whether can add layer | Elaine Huang | ["NK Facility"] | Inventory Specialist |  | 11/08/2021 | 02/28/2022 | Blocked |  |  | 0
["SmartView"] | 保稅進口明細 | Requirement Understanding | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | 保稅進口明細 | Document Preparation | Sam Chang | ["Suku Facility"] | Admin / Import & Export | Operation Owner - Jessie Lin | 10/22/2021 | 10/29/2021 | Completed |  |  | 0
["SmartView"] | 保稅進口明細 | Development | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 11/22/2021 | 12/03/2021 | Completed |  |  | 0
["SmartView"] | 保稅進口明細 | Implementation and Monitoring | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 11/25/2021 | 02/11/2022 | Completed | Nov.12 Develop the API for T1/T2 received, contact SuKu admin Judy add viewsmart@ups.com into mail loop |  | 0
["Industrial Engineering"] | 保稅進口明細 | 確認輸入欄位是不是要變少 | Jasmine Lin;Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 11/29/2021 | 12/02/2021 | Completed |  |  | 0
["Industrial Engineering"] | 保稅進口明細 | Mail Receiver Why-why analysis | Jasmine Lin | ["Suku Facility"] | Admin / Import & Export |  | 11/29/2021 | 11/29/2021 | Completed |  |  | 0
["SmartView"] | 到貨清單作業改善 | Requirement Understanding | Sam Chang | ["Suku Facility"] | Inbound / GR |  | 10/01/2021 | 10/07/2021 | Completed |  |  | 0
["SmartView"] | 到貨清單作業改善 | Document Preparation | Sam Chang | ["Suku Facility"] | Inbound / GR | Operation Owner - Nancy Shu | 10/04/2021 | 10/08/2021 | Completed |  |  | 0
["SmartView"] | 到貨清單作業改善 | Development | Sam Chang | ["Suku Facility"] | Inbound / GR |  | 10/11/2021 | 10/19/2021 | Completed |  |  | 0
["SmartView"] | 到貨清單作業改善 | Implementation and Monitoring | Sam Chang | ["Suku Facility"] | Inbound / GR |  | 10/18/2021 | 11/11/2021 | Completed |  | /:o:/g/personal/00000158790_ups_com/EiNeAhs0S85ChLqeJhyD8csBiQuQSUiG5Askeiq5USwl_A?email=cjimmy%40ups.com&e=8u957D | 0
["SmartView"] | 到貨清單作業改善 | 2nd Round Development | Sam Chang | ["Suku Facility"] | Inbound / GR | After workshop and site survey, Jimmy found more opportunity to enhance dock-in tool and process 1. Judge Bonded / Non-bond Shipment from 報單號碼 2. Assigned Location when Dock-in 3. 狀態異常貼 print out together | 10/25/2021 | 11/09/2021 | Completed |  |  | 0
["SmartView"] | 到貨清單作業改善 | 2nd Round Implementation and Monitoring | Sam Chang;Jasmine Lin | ["Suku Facility"] | Inbound / GR | already finish 2nd , wait for result | 11/08/2021 | 12/02/2021 | Completed |  |  | 0
["Industrial Engineering"] | 到貨清單作業改善 | Dock-in Tool要一個As-is的Process Flow | Jasmine Lin | ["Suku Facility"] | Inbound / GR |  | 11/05/2021 | 11/11/2021 | Completed |  |  | 0
["SmartView"] | 到貨清單作業改善 | Fixed Connection Issue to see if sync issue can be solved | Sam Chang | ["Suku Facility"] | Inbound / GR | Copy existing function to brand new excel file | 11/05/2021 | 11/09/2021 | Completed |  |  | 0
["Industrial Engineering"] | 到貨清單作業改善 | 非保品廠商考慮依英文字母、注音順序來排序 | Jasmine Lin | ["Suku Facility"] | Inbound / GR | Check if this will be better for Operation | 11/05/2021 | 11/11/2021 | Completed |  |  | 0
["SmartView"] | 大陸管制物品 - 未入庫前Alert | Requirement Understanding | Dragon Kao | ["Suku Facility"] | Admin / Import & Export | Operation Owner - Jessie Lin | 10/21/2021 | 10/21/2021 | Completed |  |  | 0
["SmartView"] | 大陸管制物品 - 未入庫前Alert | Document Prepration | Sam Chang | ["Suku Facility"] | Admin / Import & Export |  | 10/22/2021 | 10/29/2021 | Completed |  |  | 0
["SmartView"] | 大陸管制物品 - 未入庫前Alert | Development | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 11/22/2021 | 12/03/2021 | Completed |  |  | 0
["SmartView"] | 大陸管制物品 - 未入庫前Alert | Implementation and Monitoring | Dragon Kao | ["Suku Facility"] | Admin / Import & Export |  | 11/25/2021 | 02/11/2022 | Completed | Nov.12 Develop the API for T1/T2 received, contact SuKu admin Judy add viewsmart@ups.com into mail loop |  | 0
["Industrial Engineering"] | 派車 + Labeling Reengineering | Initiative Discussion | Elaine Huang | ["NK Facility"] | Outbound / GI |  | 04/18/2022 | 05/24/2022 | Completed | 5/10 Applied paid 2 dedicate HCs for labeling with additional one day to complete OP turn down proposal as it will impact KPI measurement 4/22 3 Proposal 1. RF gun with labeling function in packing 2. 1 Laptop+Printer and proceed in packing 3. Exisiting Operation 4/21 Check current material |  | 0
["Industrial Engineering"] | 派車Process Re-engineering | Define PPH |  | ["NK Facility"] | Outbound / GI |  | 02/28/2022 | 03/07/2022 | Completed | Per discuss with Kathia and time study result, reasonable PPH for “派車 process should be 37.3 shipment” Operation confirm the percentage of the item will be 揀車趟 is 70%, which means need to re-assigned pallet number is 30% |  | 1

## Sheet1
2022-05-03 | 2022-05-31 | 05/03/2022 | 05/31/2022 | 05/03/2022 | 05/03/2022 | 05/03/2022 | 05/03/2022 | 05/31/2022
2022-04-19 | 2022-06-24 | 04/19/2022 | 06/24/2022 |  |  |  | 04/19/2022 | 06/24/2022
2022-03-07 | 2022-06-27 | 03/07/2022 | 06/27/2022 |  |  |  | 03/07/2022 | 06/27/2022
2021-11-22 | 2021-12-13 | 11/22/2021 | 12/13/2021 |  |  |  | 11/22/2021 | 12/13/2021
2021-11-15 | 2021-11-16 | 11/15/2021 | 11/16/2021 |  |  |  | 11/15/2021 | 11/16/2021
2021-11-08 | 2021-11-17 | 11/08/2021 | 11/17/2021 |  |  |  | 11/08/2021 | 11/17/2021
2021-12-01 | 2021-12-17 | 12/01/2021 | 12/17/2021 |  |  |  | 12/01/2021 | 12/17/2021
2021-11-25 | 2021-11-29 | 11/25/2021 | 11/29/2021 |  |  |  | 11/25/2021 | 11/29/2021
2021-11-08 | 2021-11-22 | 11/08/2021 | 11/22/2021 |  |  |  | 11/08/2021 | 11/22/2021
2021-11-22 | 2022-02-25 | 11/22/2021 | 02/25/2022 |  |  |  | 11/22/2021 | 02/25/2022
2021-11-01 | 2022-05-27 | 11/01/2021 | 05/27/2022 |  |  |  | 11/01/2021 | 05/27/2022
2022-04-18 | 2022-05-29 | 04/18/2022 | 05/29/2022 |  |  |  | 04/18/2022 | 05/29/2022
2021-11-09 | 2021-11-10 | 11/09/2021 | 11/10/2021 |  |  |  | 11/09/2021 | 11/10/2021
2022-01-24 | 2022-05-27 | 01/24/2022 | 05/27/2022 |  |  |  | 01/24/2022 | 05/27/2022
2021-11-08 | 2021-12-10 | 11/08/2021 | 12/10/2021 |  |  |  | 11/08/2021 | 12/10/2021
2021-11-01 | 2021-11-26 | 11/01/2021 | 11/26/2021 |  |  |  | 11/01/2021 | 11/26/2021
2022-05-09 | 2022-05-11 | 05/09/2022 | 05/11/2022 |  |  |  | 05/09/2022 | 05/11/2022
2022-04-08 | 2022-04-26 | 04/08/2022 | 04/26/2022 |  |  |  | 04/08/2022 | 04/26/2022
2021-12-20 | 2022-06-02 | 12/20/2021 | 06/02/2022 |  |  |  | 12/20/2021 | 06/02/2022
2022-05-13 | 2022-05-18 | 05/13/2022 | 05/18/2022 |  |  |  | 05/13/2022 | 05/18/2022
2022-04-18 | 2022-05-16 | 04/18/2022 | 05/16/2022 |  |  |  | 04/18/2022 | 05/16/2022
2021-11-08 | 2021-11-12 | 11/08/2021 | 11/12/2021 |  |  |  | 11/08/2021 | 11/12/2021
2022-05-08 | 2022-06-03 | 05/08/2022 | 06/03/2022 |  |  |  | 05/08/2022 | 06/03/2022
2022-04-21 | 2022-06-06 | 04/21/2022 | 06/06/2022 |  |  |  | 04/21/2022 | 06/06/2022
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-10-22 | 2021-10-29 | 10/22/2021 | 10/29/2021 |  |  |  | 10/22/2021 | 10/29/2021
2021-11-25 | 2021-12-09 | 11/25/2021 | 12/09/2021 |  |  |  | 11/25/2021 | 12/09/2021
2021-12-10 | 2022-01-28 | 12/10/2021 | 01/28/2022 |  |  |  | 12/10/2021 | 01/28/2022
2021-11-08 | 2021-11-15 | 11/08/2021 | 11/15/2021 |  |  |  | 11/08/2021 | 11/15/2021
2021-11-29 | 2021-11-30 | 11/29/2021 | 11/30/2021 |  |  |  | 11/29/2021 | 11/30/2021
2021-10-25 | 2021-11-05 | 10/25/2021 | 11/05/2021 |  |  |  | 10/25/2021 | 11/05/2021
2021-11-15 | 2022-04-01 | 11/15/2021 | 04/01/2022 |  |  |  | 11/15/2021 | 04/01/2022
2022-03-03 | 2022-05-31 | 03/03/2022 | 05/31/2022 |  |  |  | 03/03/2022 | 05/31/2022
2021-11-30 | 2021-12-10 | 11/30/2021 | 12/10/2021 |  |  |  | 11/30/2021 | 12/10/2021
2021-12-20 | 2021-12-31 | 12/20/2021 | 12/31/2021 |  |  |  | 12/20/2021 | 12/31/2021
2022-01-03 | 2022-01-28 | 01/03/2022 | 01/28/2022 |  |  |  | 01/03/2022 | 01/28/2022
2022-01-17 | 2022-01-28 | 01/17/2022 | 01/28/2022 |  |  |  | 01/17/2022 | 01/28/2022
2022-01-24 | 2022-01-28 | 01/24/2022 | 01/28/2022 |  |  |  | 01/24/2022 | 01/28/2022
2021-12-20 | 2022-01-07 | 12/20/2021 | 01/07/2022 |  |  |  | 12/20/2021 | 01/07/2022
2022-01-31 | 2022-02-18 | 01/31/2022 | 02/18/2022 |  |  |  | 01/31/2022 | 02/18/2022
2022-05-06 | 2022-05-09 | 05/06/2022 | 05/09/2022 |  |  |  | 05/06/2022 | 05/09/2022
2021-12-02 | 2021-12-09 | 12/02/2021 | 12/09/2021 |  |  |  | 12/02/2021 | 12/09/2021
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-11-04 | 2021-11-11 | 11/04/2021 | 11/11/2021 |  |  |  | 11/04/2021 | 11/11/2021
2021-11-04 | 2021-11-11 | 11/04/2021 | 11/11/2021 |  |  |  | 11/04/2021 | 11/11/2021
2021-11-04 | 2021-11-09 | 11/04/2021 | 11/09/2021 |  |  |  | 11/04/2021 | 11/09/2021
2021-11-08 | 2021-11-30 | 11/08/2021 | 11/30/2021 |  |  |  | 11/08/2021 | 11/30/2021
2022-06-08 | 2022-06-24 | 06/08/2022 | 06/24/2022 |  |  |  | 06/08/2022 | 06/24/2022
2022-03-09 | 2022-06-15 | 03/09/2022 | 06/15/2022 |  |  |  | 03/09/2022 | 06/15/2022
2022-03-10 | 2022-03-10 | 03/10/2022 | 03/10/2022 |  |  |  | 03/10/2022 | 03/10/2022
2021-11-05 | 2021-11-12 | 11/05/2021 | 11/12/2021 |  |  |  | 11/05/2021 | 11/12/2021
2021-11-05 | 2021-12-17 | 11/05/2021 | 12/17/2021 |  |  |  | 11/05/2021 | 12/17/2021
2021-12-22 | 2022-03-31 | 12/22/2021 | 03/31/2022 |  |  |  | 12/22/2021 | 03/31/2022
2022-01-21 | 2022-01-26 | 01/21/2022 | 01/26/2022 |  |  |  | 01/21/2022 | 01/26/2022
2022-04-04 | 2022-04-29 | 04/04/2022 | 04/29/2022 |  |  |  | 04/04/2022 | 04/29/2022
2022-03-21 | 2022-05-27 | 03/21/2022 | 05/27/2022 |  |  |  | 03/21/2022 | 05/27/2022
2021-11-29 | 2022-01-07 | 11/29/2021 | 01/07/2022 |  |  |  | 11/29/2021 | 01/07/2022
2021-12-13 | 2021-12-14 | 12/13/2021 | 12/14/2021 |  |  |  | 12/13/2021 | 12/14/2021
2021-12-13 | 2021-12-17 | 12/13/2021 | 12/17/2021 |  |  |  | 12/13/2021 | 12/17/2021
2022-04-08 | 2022-05-27 | 04/08/2022 | 05/27/2022 |  |  |  | 04/08/2022 | 05/27/2022
2021-11-05 | 2021-11-09 | 11/05/2021 | 11/09/2021 |  |  |  | 11/05/2021 | 11/09/2021
2021-11-11 | 2021-11-12 | 11/11/2021 | 11/12/2021 |  |  |  | 11/11/2021 | 11/12/2021
2021-11-12 | 2021-11-16 | 11/12/2021 | 11/16/2021 |  |  |  | 11/12/2021 | 11/16/2021
2021-10-25 | 2021-10-29 | 10/25/2021 | 10/29/2021 |  |  |  | 10/25/2021 | 10/29/2021
2021-10-25 | 2021-10-29 | 10/25/2021 | 10/29/2021 |  |  |  | 10/25/2021 | 10/29/2021
2021-11-01 | 2021-11-22 | 11/01/2021 | 11/22/2021 |  |  |  | 11/01/2021 | 11/22/2021
2021-10-25 | 2021-11-05 | 10/25/2021 | 11/05/2021 |  |  |  | 10/25/2021 | 11/05/2021
2021-11-08 | 2021-11-23 | 11/08/2021 | 11/23/2021 |  |  |  | 11/08/2021 | 11/23/2021
2021-11-22 | 2022-06-01 | 11/22/2021 | 06/01/2022 |  |  |  | 11/22/2021 | 06/01/2022
2021-11-30 | 2021-11-30 | 11/30/2021 | 11/30/2021 |  |  |  | 11/30/2021 | 11/30/2021
2021-11-29 | 2021-12-03 | 11/29/2021 | 12/03/2021 |  |  |  | 11/29/2021 | 12/03/2021
2022-07-01 | 2022-07-15 | 07/01/2022 | 07/15/2022 |  |  |  | 07/01/2022 | 07/15/2022
2021-11-29 | 2022-01-28 | 11/29/2021 | 01/28/2022 |  |  |  | 11/29/2021 | 01/28/2022
2022-05-04 | 2022-05-16 | 05/04/2022 | 05/16/2022 |  |  |  | 05/04/2022 | 05/16/2022
2022-03-14 | 2022-06-17 | 03/14/2022 | 06/17/2022 |  |  |  | 03/14/2022 | 06/17/2022
2022-04-14 | 2022-05-23 | 04/14/2022 | 05/23/2022 |  |  |  | 04/14/2022 | 05/23/2022
2021-11-08 | 2021-12-06 | 11/08/2021 | 12/06/2021 |  |  |  | 11/08/2021 | 12/06/2021
2022-03-09 | 2022-03-21 | 03/09/2022 | 03/21/2022 |  |  |  | 03/09/2022 | 03/21/2022
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-10-21 | 2021-10-22 | 10/21/2021 | 10/22/2021 |  |  |  | 10/21/2021 | 10/22/2021
2021-11-08 | 2021-11-11 | 11/08/2021 | 11/11/2021 |  |  |  | 11/08/2021 | 11/11/2021
2021-11-10 | 2021-11-24 | 11/10/2021 | 11/24/2021 |  |  |  | 11/10/2021 | 11/24/2021
2021-11-05 | 2021-11-11 | 11/05/2021 | 11/11/2021 |  |  |  | 11/05/2021 | 11/11/2021
2021-11-01 | 2021-12-01 | 11/01/2021 | 12/01/2021 |  |  |  | 11/01/2021 | 12/01/2021
2021-11-08 | 2022-01-31 | 11/08/2021 | 01/31/2022 |  |  |  | 11/08/2021 | 01/31/2022
2021-12-01 | 2021-12-10 | 12/01/2021 | 12/10/2021 |  |  |  | 12/01/2021 | 12/10/2021
2021-11-30 | 2022-01-21 | 11/30/2021 | 01/21/2022 |  |  |  | 11/30/2021 | 01/21/2022
2021-11-03 | 2021-11-10 | 11/03/2021 | 11/10/2021 |  |  |  | 11/03/2021 | 11/10/2021
2021-11-03 | 2021-11-11 | 11/03/2021 | 11/11/2021 |  |  |  | 11/03/2021 | 11/11/2021
2022-03-21 | 2022-05-17 | 03/21/2022 | 05/17/2022 |  |  |  | 03/21/2022 | 05/17/2022
2021-11-01 | 2021-11-30 | 11/01/2021 | 11/30/2021 |  |  |  | 11/01/2021 | 11/30/2021
2021-11-04 | 2021-11-08 | 11/04/2021 | 11/08/2021 |  |  |  | 11/04/2021 | 11/08/2021
2022-03-10 | 2022-03-25 | 03/10/2022 | 03/25/2022 |  |  |  | 03/10/2022 | 03/25/2022
2021-11-08 | 2021-12-31 | 11/08/2021 | 12/31/2021 |  |  |  | 11/08/2021 | 12/31/2021
2022-05-09 | 2022-05-31 | 05/09/2022 | 05/31/2022 |  |  |  | 05/09/2022 | 05/31/2022
2021-11-08 | 2021-12-14 | 11/08/2021 | 12/14/2021 |  |  |  | 11/08/2021 | 12/14/2021
2021-11-22 | 2021-12-17 | 11/22/2021 | 12/17/2021 |  |  |  | 11/22/2021 | 12/17/2021
2021-11-22 | 2021-12-21 | 11/22/2021 | 12/21/2021 |  |  |  | 11/22/2021 | 12/21/2021
2022-05-24 | 2022-06-07 | 05/24/2022 | 06/07/2022 |  |  |  | 05/24/2022 | 06/07/2022
2021-12-01 | 2022-02-28 | 12/01/2021 | 02/28/2022 |  |  |  | 12/01/2021 | 02/28/2022
2021-12-01 | 2022-02-28 | 12/01/2021 | 02/28/2022 |  |  |  | 12/01/2021 | 02/28/2022
2021-11-25 | 2021-12-08 | 11/25/2021 | 12/08/2021 |  |  |  | 11/25/2021 | 12/08/2021
2021-11-29 | 2021-12-08 | 11/29/2021 | 12/08/2021 |  |  |  | 11/29/2021 | 12/08/2021
2021-11-08 | 2021-11-09 | 11/08/2021 | 11/09/2021 |  |  |  | 11/08/2021 | 11/09/2021
2022-02-06 | 2022-06-30 | 02/06/2022 | 06/30/2022 |  |  |  | 02/06/2022 | 06/30/2022
2021-11-08 | 2021-12-03 | 11/08/2021 | 12/03/2021 |  |  |  | 11/08/2021 | 12/03/2021
2021-11-19 | 2021-12-03 | 11/19/2021 | 12/03/2021 |  |  |  | 11/19/2021 | 12/03/2021
2021-11-15 | 2022-02-11 | 11/15/2021 | 02/11/2022 |  |  |  | 11/15/2021 | 02/11/2022
2022-01-19 | 2022-01-28 | 01/19/2022 | 01/28/2022 |  |  |  | 01/19/2022 | 01/28/2022
2022-01-23 | 2022-03-25 | 01/23/2022 | 03/25/2022 |  |  |  | 01/23/2022 | 03/25/2022
2021-11-08 | 2022-02-28 | 11/08/2021 | 02/28/2022 |  |  |  | 11/08/2021 | 02/28/2022
2021-11-05 | 2022-04-26 | 11/05/2021 | 04/26/2022 |  |  |  | 11/05/2021 | 04/26/2022
2021-11-08 | 2021-11-12 | 11/08/2021 | 11/12/2021 |  |  |  | 11/08/2021 | 11/12/2021
2021-11-08 | 2021-11-11 | 11/08/2021 | 11/11/2021 |  |  |  | 11/08/2021 | 11/11/2021
2021-11-12 | 2021-12-06 | 11/12/2021 | 12/06/2021 |  |  |  | 11/12/2021 | 12/06/2021
2022-01-03 | 2022-01-14 | 01/03/2022 | 01/14/2022 |  |  |  | 01/03/2022 | 01/14/2022
2022-04-25 | 2022-05-10 | 04/25/2022 | 05/10/2022 |  |  |  | 04/25/2022 | 05/10/2022
2021-11-08 | 2021-11-08 | 11/08/2021 | 11/08/2021 |  |  |  | 11/08/2021 | 11/08/2021
2021-11-08 | 2021-11-22 | 11/08/2021 | 11/22/2021 |  |  |  | 11/08/2021 | 11/22/2021
2022-01-11 | 2022-01-18 | 01/11/2022 | 01/18/2022 |  |  |  | 01/11/2022 | 01/18/2022
2022-01-19 | 2022-01-25 | 01/19/2022 | 01/25/2022 |  |  |  | 01/19/2022 | 01/25/2022
2022-01-20 | 2022-01-25 | 01/20/2022 | 01/25/2022 |  |  |  | 01/20/2022 | 01/25/2022
2022-01-19 | 2022-01-26 | 01/19/2022 | 01/26/2022 |  |  |  | 01/19/2022 | 01/26/2022
2022-01-19 | 2022-01-26 | 01/19/2022 | 01/26/2022 |  |  |  | 01/19/2022 | 01/26/2022
2021-11-08 | 2021-11-26 | 11/08/2021 | 11/26/2021 |  |  |  | 11/08/2021 | 11/26/2021
2021-11-15 | 2021-11-26 | 11/15/2021 | 11/26/2021 |  |  |  | 11/15/2021 | 11/26/2021
2021-11-22 | 2022-02-25 | 11/22/2021 | 02/25/2022 |  |  |  | 11/22/2021 | 02/25/2022
2021-11-08 | 2021-11-29 | 11/08/2021 | 11/29/2021 |  |  |  | 11/08/2021 | 11/29/2021
2021-11-01 | 2021-11-05 | 11/01/2021 | 11/05/2021 |  |  |  | 11/01/2021 | 11/05/2021
2021-11-08 | 2021-11-09 | 11/08/2021 | 11/09/2021 |  |  |  | 11/08/2021 | 11/09/2021
2021-11-08 | 2021-12-07 | 11/08/2021 | 12/07/2021 |  |  |  | 11/08/2021 | 12/07/2021
2021-11-08 | 2021-11-09 | 11/08/2021 | 11/09/2021 |  |  |  | 11/08/2021 | 11/09/2021
2021-12-21 | 2022-05-27 | 12/21/2021 | 05/27/2022 |  |  |  | 12/21/2021 | 05/27/2022
2021-11-19 | 2022-02-28 | 11/19/2021 | 02/28/2022 |  |  |  | 11/19/2021 | 02/28/2022
2022-03-01 | 2022-06-06 | 03/01/2022 | 06/06/2022 |  |  |  | 03/01/2022 | 06/06/2022
2021-11-08 | 2021-11-26 | 11/08/2021 | 11/26/2021 |  |  |  | 11/08/2021 | 11/26/2021
2021-11-08 | 2021-11-19 | 11/08/2021 | 11/19/2021 |  |  |  | 11/08/2021 | 11/19/2021
2021-11-08 | 2021-12-02 | 11/08/2021 | 12/02/2021 |  |  |  | 11/08/2021 | 12/02/2021
2021-11-11 | 2021-11-15 | 11/11/2021 | 11/15/2021 |  |  |  | 11/11/2021 | 11/15/2021
2021-11-15 | 2021-11-22 | 11/15/2021 | 11/22/2021 |  |  |  | 11/15/2021 | 11/22/2021
2021-11-15 | 2021-11-18 | 11/15/2021 | 11/18/2021 |  |  |  | 11/15/2021 | 11/18/2021
2021-11-18 | 2022-03-22 | 11/18/2021 | 03/22/2022 |  |  |  | 11/18/2021 | 03/22/2022
2021-12-01 | 2022-06-03 | 12/01/2021 | 06/03/2022 |  |  |  | 12/01/2021 | 06/03/2022
2022-01-11 | 2022-07-15 | 01/11/2022 | 07/15/2022 |  |  |  | 01/11/2022 | 07/15/2022
2021-11-05 | 2021-11-19 | 11/05/2021 | 11/19/2021 |  |  |  | 11/05/2021 | 11/19/2021
2022-04-14 | 2022-05-03 | 04/14/2022 | 05/03/2022 |  |  |  | 04/14/2022 | 05/03/2022
2022-05-04 | 2022-07-29 | 05/04/2022 | 07/29/2022 |  |  |  | 05/04/2022 | 07/29/2022
2022-05-02 | 2022-07-29 | 05/02/2022 | 07/29/2022 |  |  |  | 05/02/2022 | 07/29/2022
2022-05-10 | 2022-06-17 | 05/10/2022 | 06/17/2022 |  |  |  | 05/10/2022 | 06/17/2022
2021-11-11 | 2021-11-12 | 11/11/2021 | 11/12/2021 |  |  |  | 11/11/2021 | 11/12/2021
2022-05-09 | 2022-05-23 | 05/09/2022 | 05/23/2022 |  |  |  | 05/09/2022 | 05/23/2022
2022-03-04 | 2022-04-29 | 03/04/2022 | 04/29/2022 |  |  |  | 03/04/2022 | 04/29/2022
2021-11-22 | 2021-11-22 | 11/22/2021 | 11/22/2021 |  |  |  | 11/22/2021 | 11/22/2021
2021-11-25 | 2022-05-27 | 11/25/2021 | 05/27/2022 |  |  |  | 11/25/2021 | 05/27/2022
2021-11-08 | 2021-11-09 | 11/08/2021 | 11/09/2021 |  |  |  | 11/08/2021 | 11/09/2021
2021-11-08 | 2022-02-28 | 11/08/2021 | 02/28/2022 |  |  |  | 11/08/2021 | 02/28/2022
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-10-22 | 2021-10-29 | 10/22/2021 | 10/29/2021 |  |  |  | 10/22/2021 | 10/29/2021
2021-11-22 | 2021-12-03 | 11/22/2021 | 12/03/2021 |  |  |  | 11/22/2021 | 12/03/2021
2021-11-25 | 2022-02-11 | 11/25/2021 | 02/11/2022 |  |  |  | 11/25/2021 | 02/11/2022
2021-11-29 | 2021-12-02 | 11/29/2021 | 12/02/2021 |  |  |  | 11/29/2021 | 12/02/2021
2021-11-29 | 2021-11-29 | 11/29/2021 | 11/29/2021 |  |  |  | 11/29/2021 | 11/29/2021
2021-10-01 | 2021-10-07 | 10/01/2021 | 10/07/2021 |  |  |  | 10/01/2021 | 10/07/2021
2021-10-04 | 2021-10-08 | 10/04/2021 | 10/08/2021 |  |  |  | 10/04/2021 | 10/08/2021
2021-10-11 | 2021-10-19 | 10/11/2021 | 10/19/2021 |  |  |  | 10/11/2021 | 10/19/2021
2021-10-18 | 2021-11-11 | 10/18/2021 | 11/11/2021 |  |  |  | 10/18/2021 | 11/11/2021
2021-10-25 | 2021-11-09 | 10/25/2021 | 11/09/2021 |  |  |  | 10/25/2021 | 11/09/2021
2021-11-08 | 2021-12-02 | 11/08/2021 | 12/02/2021 |  |  |  | 11/08/2021 | 12/02/2021
2021-11-05 | 2021-11-11 | 11/05/2021 | 11/11/2021 |  |  |  | 11/05/2021 | 11/11/2021
2021-11-05 | 2021-11-09 | 11/05/2021 | 11/09/2021 |  |  |  | 11/05/2021 | 11/09/2021
2021-11-05 | 2021-11-11 | 11/05/2021 | 11/11/2021 |  |  |  | 11/05/2021 | 11/11/2021
2021-10-21 | 2021-10-21 | 10/21/2021 | 10/21/2021 |  |  |  | 10/21/2021 | 10/21/2021
2021-10-22 | 2021-10-29 | 10/22/2021 | 10/29/2021 |  |  |  | 10/22/2021 | 10/29/2021
2021-11-22 | 2021-12-03 | 11/22/2021 | 12/03/2021 |  |  |  | 11/22/2021 | 12/03/2021
2021-11-25 | 2022-02-11 | 11/25/2021 | 02/11/2022 |  |  |  | 11/25/2021 | 02/11/2022
2022-04-18 | 2022-05-24 | 04/18/2022 | 05/24/2022 |  |  |  | 04/18/2022 | 05/24/2022
2022-02-28 | 2022-03-07 | 02/28/2022 | 03/07/2022 |  |  |  | 02/28/2022 | 03/07/2022